## Evidence Tracker
ID | Feature | Status | Developer | Test | Screenshot | Log/Output | README | Technical Doc | PPT Slide | Notes
F-01 | User registration/login | TESTED | Subhranil | Passed |  |  | Done | Done
F-02 | JWT auth (RS256) | TESTED | Subhranil | Passed |  |  | Done | Done |  | RSA key-pair signing
F-03 | RBAC (4 roles) | TESTED | Subhranil | Passed |  |  | Done | Done |  | Only /me + 1 test route protected initially
F-04 | Admin user management | TESTED | Subhranil | Passed |  |  | Pending | Done |  | List users, update roles
F-05 | Workstation Center creation | TESTED | Subhranil | Passed |  |  | Pending | Done |  | Blocked earlier by stale Mongo index, fixed
F-06 | Bulk employee assignment | TESTED | Subhranil | Passed |  |  | Pending | Done
F-07 | Role-based center access / duplicate-assignment checks | IN PROGRESS | Subhranil | Ran, result unconfirmed |  |  | Pending | Done |  | Needs dev confirmation
F-08 | Automated auth tests (Jest/Supertest) | TESTED | Subhranil | Passed |  |  | N/A | Done |  | 6 cases, dedicated test DB
F-09 | Frontend app (React) - auth, dashboards, workstation UI | TESTED | Vishal | Passed |  |  | Pending | Done |  | Manual testing
F-10 | Sanitization Request form + validation | TESTED | Vishal | Passed |  |  | Pending | Done |  | Mock submission only, backend pending
F-11 | Desktop UI (Login/Dashboard, Qt) | TESTED | Ansh Pandey | Passed |  |  | Pending | Done |  | UI only, no backend integration
F-12 | StorageDevice class | TESTED | Subhranil | Passed |  |  | N/A | Done
F-13 | StorageManager class | TESTED | Subhranil | Passed |  |  | N/A | Done
F-14 | Desktop CMake build config | TESTED | Subhranil | Passed |  |  | N/A | Done
F-15 | Windows physical device discovery | TESTED | Subhranil | Passed |  |  | Pending | Done |  | Now detects real hardware, not just sample data
F-16 | Device classification (HDD/SSD, bus type, internal/removable) | IN PROGRESS | Subhranil | Partial |  |  | Pending | Done |  | Bus/device/media-type logic now exists, uses seek-penalty heuristic, not fully reliable yet
F-17 | Capability Detection / Sanitization / Verification / Certificates | PLANNED | Subhranil | - |  |  | Pending | - |  | Not started
F-18 | Safety Engine foundation | IN PROGRESS | Subhranil | Partial | [5 empty] | System-disk + physical-device checks partially working, boot/mounted-volume/OS-dependency not implemented
F-19 | Qt Desktop | TESTED | Subhranil | Passed

## How To Use
HOW TO USE THIS TRACKER
Every feature/module gets one row. Status: DONE, TESTED, IN PROGRESS, or PLANNED - ask the developer, never guess.
Fill Screenshot/Log columns with the actual filename once evidence is saved.
README/Technical Doc/PPT Slide columns say Pending until that section is actually written.
Update this daily. If a feature isn't in here, it will get forgotten when writing the README or PPT.